## Slide 1
1. Project Initiation
Q1 17/18
Develop Project Charter
Develop Project Plan Draft
Baseline Schedule
Develop Master Project Plan
Change, Risk, Issue, Procurement, Schedule, Scope, Quality, Stakeholder, Communication Management
4. Management and Control
4.1 Project Management and Control (PMBoK Process)
2. Project Planning
Complete Project Planning
MHR, PPR, CORBS Requirements (Buy/Build
BC Online Replacement Requirements / Options Analysis
Workshops and Requirements Alignment with Partners
COLIN & NRO Requirements
Plan MVP with Project Partners
Vendor Procurement (RFP Process)
3. Project Execution
Build MVP for Registries Apps to integrate to: IDIM, MyGovBC, PayBC, COLIN/NRP API
Deploy Pilot MVP
Pilot MVP with partners – gain feedback from business units – I&A model
Integrate SBC Registries Applications to PayBC IDIM, MyGovBC
Develop new Applications (Replace MHR,PPR,COBRS)
COLIN/NRO API development
Develop Process Governance for new operating model
Data Mapping / Data Conversion
Full End to End UAT, System, Integration Testing / QA
5. Project Closing
Q2 17/18
Q3 17/18
Q4 17/18
Q1 18/19
Q2 18/19
Q3 18/19
Q4 18/19
Q1 19/20
Q2 18/19
Q3 18/19
Q4 18/19
Q1 19/20
Q2 19/20
Q3 19/20
Q4 19/20
Q1 20/21
Project Closeout, Benefits Mgmt and Lessons Learned
Handover to Ops Sustainment Team
2.2
2.3
2.4
3.1
3.2
A M J
J A S
O N D
J F M
A M J
J A S
O N D
J F M
A M J
J A S
O N D
J F M
A M J
J A S
O N D
J F M
A M J
Gate 0
Analysis
Gate 1
Planning & Design
Gate 2
Development and Migration
Gate 3
Testing & QA
Q2 20/21
Q3 20/21
Q4 20/21
J A S
O N D
J F M
Gate 4
Implementatio/ Go-Live
3.4
3.5
3.3
3.6
3.7
3.8
3.9
Final Conversion & Go-Live March 31, 2021
Mainframe Migration Registries Applications Sub-Milestone Chart
2.7

## Slide 2
1. Project Initiation
Q1 17/18
Develop Project Charter
Develop Project Plan Draft
Baseline Initial Schedule
Develop Initial Master Project Plan
Change, Risk, Issue, Procurement, Schedule, Scope, Quality, Stakeholder, Communication Management
4. Management and Control
4.1 Project Management and Control (PMBoK Process)
2. Project Planning
Complete Project Planning
GARMS Integration to CAS Only MVP Requirements
GARMS System to System MVP Requirements
GARMS Front Counter System MVP Requirements
GARMS Workshops and Requirements Alignment with Ministry & Private Partners
GARMS Front Counter Full Requirements
Vendor Procurement (RFP Process)
3. Project Execution
Build CAS Integration MVP
Build System to System MVP
Build Front Counter System MVP
Build Complete Front Counter System
Develop Process Governance for new operating model
Data Mapping Development / Data Conversion
Full End to End UAT, System, Integration Testing / QA
User and Admin Training
Onboard Users
5. Project Closing
Q2 17/18
Q3 17/18
Q4 17/18
Q1 18/19
Q2 18/19
Q3 18/19
Q4 18/19
Q1 19/20
Q2 18/19
Q3 18/19
Q4 18/19
Q1 19/20
Q2 19/20
Q3 19/20
Q4 19/20
Q1 20/21
Project Closeout, Benefits Management and Lessons Learned
Handover to Ops Sustainment Team
2.5
3.1
A M J
J A S
O N D
J F M
A M J
J A S
O N D
J F M
A M J
J A S
O N D
J F M
A M J
J A S
O N D
J F M
A M J
Gate 0
Analysis
Gate 1
Planning & Design
Gate 2
Development and Migration
Gate 3
Testing & QA
Q2 20/21
Q3 20/21
Q4 20/21
J A S
O N D
J F M
Gate 4
Implementatio/ Go-Live
2.6
3.4
3.6
3.7
Final Conversion & Go-Live March 31, 2021
Mainframe Migration
GARMS Sub-Milestone Chart
2.3
2.4
3.2
3.3
3.5
3.8
3.9
2.7